## EEE381 IIP Gantt Chart SEM 1
PROJECT TITLE | Implementation of an Arithmetic Unit based on approximate computing for RISC-V SoC
PROJECT SUPERVISOR | Mr Neil Powell
TASK | TASK | START | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | WEEK | IN WEEKS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project workspace intialisation |  |  | 100%
1.1.1 | Set up workspace - Git | 1 | 1 | 100%
1.1.2 | Install and build required tools - Vivado/VSCode | 1 | 1 | 100%
1.2 | Background research & Literature review |  |  | 72%
1.2.1 | Research approximate computing methods | 2 | 3 | 82%
1.2.2 | RISC-V based approximations | 3 | 1 | 100%
1.2.3 | FPGA based approximations - (Project Motivation) | 3 | 3 | 65%
1.2.4 | Discuss reading material with supervisor | 2 | 3 | 80%
1.3 | Project Initialisation Document - PID |  |  | 85%
1.3.1 | Draft PID for marking by supervisor | 3 | 2 | 100%
1.3.2 | PID submission [M1] | 4 | 0 | 70%
2 | Project specifics and design planning
2.1 | Plan project specification [M2] | 5 | 1 | 0%
2.2 | Design project modules | 5 | 1 | 0%
2.2.1 | Research implementing MAC on FPGA | 5 | 1 | 0%
2.2.2 | FPGA modules (MAC… etc) | 5 | 1 | 0%
2.2.3 | Consider final approximation method for the project [M3] | 5 | 1 | 0%
3 | Project design implementation (modular)
3.1 | Implement project modules in FPGA | 7 | 2 | 0%
3.2 | Implement approximation method chosen in FPGA [M4] | 8 | 1 | 0%
3.3 | Cross reference specification | 9 | 1 | 0%
4 | Project design testing - Unit Testing
4.1 | Design testbenches for all modules | 9 | 2 | 0%
4.1.1 | Test edgecases | 10 | 1 | 0%
4.1.2 | Check limitations | 10 | 1 | 0%
4.1.3 | Conduct performance evaluation (speed, memory) | 10 | 1 | 0%
5 | Interim Report
5.1 | Prepare and plan draft for the interim report | 7 | 5 | 0%
5.2 | Produce final report for submission in LateX [M5] | 10 | 2 | 0%
6 | Public Engagement Presentation
6.1 | Plan pitch for presentation | 10 | 1 | 0%
6.2 | Prepare slides and material for presentation | 10 | 1 | 0%

## EEE381 IIP Gantt Chart SEM 2
PROJECT TITLE | Implementation of an Arithmetic Unit based on approximate computing for RISC-V SoC
PROJECT SUPERVISOR | Mr Neil Powell
DATE | 2024-10-10
[5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | START | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | WEEK | IN WEEKS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project workspace intialisation |  |  | 0%
1.1.1 | Set up workspace - Git |  |  | 0%
1.1.2 | Install and build required tools - Vivado/VSCode |  |  | 0%
1.2 | Background research & Literature review |  |  | 0%
1.2.1 | Research approximate computing methods |  |  | 0%
| Discuss reading material with supervisor |  |  | 0%
| Project Initialisation Document - PID |  |  | 0%
| Draft PID for marking by supervisor |  |  | 0%
Project Definition and Planning
| Scope & Goal Setting |  |  | 0%
| Budget |  |  | 0%
| Communication Plan |  |  | 0%
| Risk Management |  |  | 0%
Project Launch and Execution
| Status & Tracking |  |  | 0%
| KPIs |  |  | 0%
| Monitoring |  |  | 0%
| Forecasts |  |  | 0%
| Project Updates |  |  | 0%
| Chart Updates |  |  | 0%
Project Performance / Monitoring
| Project Objectives |  |  | 0%
| Quality Deliverables |  |  | 0%
| Effort and Cost Tracking |  |  | 0%
| Project Performance |  |  | 0%