## EEE381 IIP Gantt Chart SEM 1
PROJECT TITLE | Implementation of an Arithmetic Unit based on approximate computing for RISC-V SoC
PROJECT SUPERVISOR | Mr Neil Powell
TASK | TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project workspace intialisation
1.1.1 | Set up workspace - Git
1.1.2 | Install and build required tools - Vivado/VSCode
1.2 | Background research & Literature review
1.2.1 | Research approximate computing methods
1.2.2 | RISC-V based approximations
1.2.3 | FPGA based approximations - (Project Motivation)
1.2.4 | Document researched material
1.3 | Project Initialisation Document - PID
1.3.1 | Draft PID for marking by supervisor
1.3.2 | PID submission [M1]
2 | Project specifics and design planning
2.1 | Plan project specification [M2]
2.2 | Design project modules
2.2.1 | Research implementing MAC on FPGA
2.2.2 | FPGA modules (MAC… etc)
2.2.3 | Consider final approximation method for the project [M3]
3 | Project design implementation (modular)
3.1 | Implement project modules in FPGA
3.2 | Cross reference specification
4 | Interim Report
4.1 | Prepare and plan draft for the interim report
5 | Public Engagement Presentation
5.1 | Plan pitch for presentation
5.2 | Prepare slides and material for presentation

## EEE381 IIP Gantt Chart SEM 2
PROJECT TITLE | Implementation of an Arithmetic Unit based on approximate computing for RISC-V SoC
PROJECT SUPERVISOR | Mr Neil Powell
TASK | TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project design implementation
1.1 | Design schematics and block diagrams
1.2 | Implement approximation method chosen in FPGA [M4]
1.3 | Cross reference specification
1.4 | Consult peer review
2 | Simulation Testing - Unit Testing
2.1 | Create simulation testbenches for all modules
2.2 | Assess performance and funtionality
2.3 | Determine performance metrics
3 | RISC-V Integration
3.1 | Research into RISC-V implementation
3.2 | Integrate approximate MAC unit into RISC-V SoC
4 | Evaluation & Analysis - Integration Testing (approximation)
4.1 | Design testbenches for integrated modules
4.2 | Test edgecases
4.3 | Check limitations
4.4 | Conduct performance evaluation (speed, memory)
5 | Report & Presentation
5.1 | Initial report writeup
5.2 | Final report